## Estimates.CSV (Challenges) - Sh
Story | Task | Estimate min (hr) | Estimate max (hr) | Actual | Comment
Ingestion pipeline | Write ingestion pseudocode and architecture plan | 0.5 | 1.5
Project setup | Create github repository and setup project | 0.5 | 1 | 15 minutes | Created basic structure of the project
VectorDB setup | Setup ChromaDB | 1 | 2
Embeddings | Create embeddings using LLM | 2 | 3
ChatBot | Create ChatBot to give user query | 2 | 3
Similarity check | Check the similarity of the embeddings using Cosine similarity | 2 | 3
Final output | Get the final output from after similarity check | 1 | 3
Generate summary | Generate the summary of the output | 2 | 3
Build API for upload | Endpoints for uploading and storing chunks | 1 | 2
Build API for similarity check | Similarity search endpoint to query documents | 1 | 2
Build API for get | endpoint to get details of specific journal when requested | 1 | 2