## Estimates.CSV (Challenges) - Sh
Story | Task | Estimate min (hr) | Estimate max (hr) | Actual | Comment
Ingestion pipeline | Write ingestion pseudocode and architecture plan | 0.5 | 1.5 | 1 hour | Pseudo code for ingestion pipeline and explanation is give in the ingestion_pipeline markdown file.
Project setup | Create github repository and setup project | 0.5 | 1 | 15 minutes | Created basic structure of the project
VectorDB setup | Setup ChromaDB | 1 | 2 | 10 minutes | Installed the required libraries and initiated the DB
Embeddings | Create embeddings using LLM/Sentence Transformer | 2 | 3 | 10 minutes | Created two approaches to get the embedding. One with Open AI embedding model and the another with Sentence Transformer. Since Open AI's embedding model is paid, we can go with the Sentence Transformer which is free of cost.
ChatBot | Create ChatBot to give user query | 2 | 3 | 1 hour | The chatbot answers research questions based on semantic search from uploaded journal chunks. It shows the answer, top 5 citations with metadata and links, and a usage chart. The answer is LLM generated by understanding the context and rewriting in its own words.
Similarity check | Check the similarity of the embeddings using Cosine similarity | 2 | 3 | 10 minutes | ChromaDB's default way of checking similarity is using Cosine Similarity.
Final output | Get the final output from after similarity check | 1 | 3 | 10 minutes | Done in Postman
Generate summary | Generate the summary of the user input document | 2 | 3 | 30 minutes | It will generate the summary of the selected document with the help of Open AI's GPT
Compare documents | Compare two different documents selected by the user | 2 | 3 | 30 minutes | It will compare the two documents selected by the user. It also uses the OpenAI's GPT
Build API for upload | Endpoints for uploading and storing chunks | 1 | 2 | 45 minutes | For creating and testing using Postman, Made changes in uploading json from file url and also using chunks
Build API for similarity check | Similarity search endpoint to query documents | 1 | 2 | 45 minutes | For creating and testing using Postman, Made changes in the response which took some time to debug
Build API for get | endpoint to get details of specific journal when requested | 1 | 2 | 30 minutes
Readme.md | Creating readme.md explaining the pipeline | 1 | 2 | 1 hour
Extra features | Creating extra_features.md | 1 | 2 | 30 minutes